## Anskaffelser Legemidler
Revidert: 1. april 2024
(Ikke endre)Anskaffelse | (Ikke endre)Radkontrollsum | (Ikke endre)Endret den | Anskaffelse ID | Anskaffelsenavn | Prosjektleder | Fagrådgiver | Prosjektstart | Kunngjøring | Tildeling | Avtalestart
67df175e-a9bf-eb11-bacc-000d3a3a8a55 | rPdOJesiwrtAYk1WGYD3IzIxf3mz1yTLB8JuXXQTWViR593sH7Uvc3V7aXgEQ9Bt0qjArS4gZwcRunQpPfn+eg== | 2024-02-20 09:21 | 2501h | Klorheksidin | Eirik Sverrisson | Gudrun Gudnadottir | 2022-02-15 | 2023-11-08 | 2024-01-26 | 2024-04-01
e6d40c40-d568-ee11-9ae7-6045bd895897 | XOX8cQBzXaRSJGoKNgav5zsHHUGZMwcNP3gUtcUHXJhDE5TOG65kZeZRPyklL3SrtfWF20gKvj+hURJlreb8dg== | 2024-02-20 09:20 | 2301a-2 | Benzylpenicillin | Eirik Sverrisson | Gudrun Gudnadottir | 2023-10-12 | 2023-11-08 | 2024-01-11 | 2024-04-01
b8742a6e-1751-eb11-a812-000d3aacb5df | /gpz44Ft5EvfH2Mj5BXaqR2aiEAXuSXtUdoQ6dkxoyYxjhEmL9nAFyO2ncYr7JSEilQ54hlF8Z6LM4n8CY23oQ== | 2024-01-06 12:20 | Nordisk | Nordisk 2024 | Eirik Sverrisson | Pål Rydstrøm | 2022-08-15 | 2023-10-05 | 2023-11-23 | 2024-04-01
fea71f83-3372-ed11-9561-6045bd895243 | ol0FaKy7RvEKYJb6IcP1CPUwJWT0sBx9N0Px36sdVGtkMVOw05aHUV6wn8LRDGScsCiuWwSDDK5R3yQ+AXzGVQ== | 2024-02-19 08:11 | 2406b | TNF BIO uten biotilsvarende konkurranse | Eirik Sverrisson | Pål Rydstrøm | 2022-11-01 | 2023-12-12 | 2024-04-15 | 2024-05-01
529f7d2c-f752-ee11-be6e-6045bd895444 | MBUsczH3qEyNmNMNB0iS1Wqrk8vBXh+OBK/aatkdkUmC4kZu2RuiqKRXFOSPEBw+uXbXpU2sm8BnJ2cIGxrb7Q== | 2024-02-12 14:54 | 2499m | Sapropterin | Per Ivar Rivenæs | Tonje Marie Lukkassen | 2023-09-01 | 2023-09-23 | 2023-11-03 | 2024-05-01
9d9ec433-5300-ee11-8f6e-6045bd929f12 | Ek25QTBKsDnZgvrBPGcNekMnObg8RW0C33gKB+Drd2bJNY/XAdU2H9wfBMv7lfdFDiGpOh0Wyco40j3Zd7xVvA== | 2024-02-12 14:55 | 2499f | Idiopatisk lungefibrose (IPF) | Per Ivar Rivenæs | Tonje Marie Lukkassen | 2023-05-01 | 2023-09-16 | 2023-10-27 | 2024-05-01
42e13562-a9bf-eb11-bacc-000d3a3a87fe | iN7YXgaGJU4JYGti7tLNm0IMK2MFbzAM+yZAzan2iDKNTwuOtefvUwK2xZQH6LfdyQfvqeJs0i/ddccFb/nRFA== | 2024-02-12 14:54 | 2422 | Plasmaderiverte legemidler SCIG, Albumin og Octaplasma | Per Ivar Rivenæs | Erik Hviding | 2023-04-20 | 2023-09-25 | 2023-11-20 | 2024-06-01
429ebe3c-f3a5-ec11-983f-00224884cbcd | 2F3HEwLxhse7606n3fatRVxqSylllARqcLiRleWMRMp8EqKE26DJS/Fek5u2tmGvWCLqiYIKzueA1XHOm9kDGA== | 2024-02-14 11:43 | 2430 | Kronisk nyresykdom, anemi og elektrolyttforstyrrelser | Lars Hjellup | Anne Helen Ognøy | 2023-04-17 | 2023-09-15 | 2023-11-17 | 2024-06-01
11df175e-a9bf-eb11-bacc-000d3a3a8a55 | lOmpPUtpuqurA4t2a9E6hKI4lGZPkEfSPR823LA1M4rBPWLIm05qxd73sRV1+f44abUVg41d33bEXIO5u4eTMA== | 2024-03-05 12:57 | 2416 | Alvorlig astma | Per Ivar Rivenæs | Pål Rydstrøm | 2023-05-24 | 2023-12-12 | 2024-03-05 | 2024-09-01
1fdf175e-a9bf-eb11-bacc-000d3a3a8a55 | yJf+1WaDKiyDh0zFmdk1iWWYtUKLt1Z6OcxxZasydGnZuSGwUq6S91ak2h7uR5rXzviyl9AiZSi3EaGWtCoxjg== | 2024-03-05 12:56 | 2499l | ITP (Idiopatisk trombocytopenisk purpura) | Per Ivar Rivenæs | Tonje Marie Lukkassen | 2023-06-01 | 2023-12-12 | 2024-02-21 | 2024-09-01
3e8903b0-cbfa-ed11-8849-6045bd929f12 | 9BRWC8FtI4DxI5dMTe9TpPuh7ALTg/dXwrdt5OKWRXCH4rRT5ZQLw+rhKMHhn+ExIepltLV+3s2i/lnuEDGAGQ== | 2024-02-22 12:25 | 2409b | Nevroendokrine svulster | Per Ivar Rivenæs | Pål Rydstrøm | 2023-06-01 | 2023-12-12 | 2024-02-02 | 2024-09-01
47590866-f889-ee11-8179-6045bd895897 | 1mZAYGdjwpDXCWWM/GrKdZIq839jCXW0bB4NJPjV9mdQZtz8jeszVYXMTXVhVEsuCXRMkEfFw+ZqzjSsTu8UpQ== | 2024-02-26 09:16 | 2412 | Blodkoagulasjonsfaktorer | Lars Hjellup | Erik Hviding | 2023-11-01 | 2023-12-19 | 2024-02-26 | 2024-09-01
8287bec4-4d50-ed11-bba2-6045bd895c76 | Wln3Br7k9NJMpicswsHfk4qg3PynsHnlG+u5qxHDPO5J6lCPCRP551AwvjzHCnPhkJijj+y6zpBbOu7/bdcvlA== | 2024-02-20 09:22 | 2407g | Diverse ikke-parenterale kjemoterapeutika | Eirik Sverrisson | Maja Monsen | 2022-10-03 | 2023-05-10 | 2023-10-27 | 2024-10-01
cb50362f-b671-ee11-8179-6045bd895897 | pObsgdUp5wTFSeZAb/z2Wze0MsGWQFTBthZOtko3n9jL8lA5Kuwo6k/zghyiaQP56RspUuuirfUs5wmnxnXMFw== | 2024-03-13 08:49 | 2407 | Onkologi | Per Ivar Rivenæs | Helle Nærsnes Endresen | 2023-10-16 | 2024-02-06 | 2024-04-04 | 2024-10-01
fbac974f-5050-ed11-bba2-6045bd895c76 | JrNnayo7FISJnWTcB8lIKkNJYgOLUZ6UrTsa/DiKM5BSxmHQiMRYSB0kxM37KL8UzawkDK8LC0WUgN/HI60axw== | 2024-02-12 11:47 | 2407j | Diverse kjemoterapeutika - til inf inj | Eirik Sverrisson | Maja Monsen | 2022-10-03 | 2023-05-10 | 2023-10-27 | 2024-10-01
3605ff61-96d0-ee11-9079-6045bd895444 | YBky+j0pfJTbALGatfJGfZq4JufHFoDIVeedYR2GskZfRBQngLH0QxPUxA6J+bvGHbb6cHGB/XaUGwC5NPxsyQ== | 2024-03-13 08:49 | 2414a | PAH Treprostinil | Per Ivar Rivenæs | Pål Rydstrøm | 2023-02-15 | 2023-12-19 | 2024-02-15 | 2024-10-01
36835625-9d61-ed11-9561-6045bd895bb0 | ZmGbSJIt9ktS49N7nDoW39emMW9eyw7TgUiJfqhOO2lkRUUQjjFQqs1Bu9zZR4a/I5DTnJwtc6ogRLwNKlJB8Q== | 2024-03-12 14:00 | 2502 | Kontrastmidler | Lars Hjellup | Gudrun Gudnadottir | 2022-12-12 | 2024-01-07 | 2024-03-22 | 2024-11-01
51df175e-a9bf-eb11-bacc-000d3a3a8a55 | dCOfffr9NbrbCeruMa/90FAgygu9HOYxmo8D6sLVhejJdOoqOfF4KWKwThGS2RSnNdhkAtIxty57Bs0oW7HNLg== | 2024-03-11 10:19 | 2501a | Antiinfektiver - diverse | Eirik Sverrisson | Maja Monsen | 2022-10-24 | 2023-09-14 | 2024-03-08 | 2025-02-01
58df175e-a9bf-eb11-bacc-000d3a3a8a55 | oegjtUNje1i9PgkG5P2sgQKQVhGn6ixXa+i8kUu+oKBSWB7mvRlTXT/vrWDHC2AyGXGjW6T366gj30b046fzgw== | 2024-03-07 09:38 | 2501b | Ikke-parenterale legemidler - diverse | Eirik Sverrisson | Maja Monsen | 2022-10-24 | 2023-10-25 | 2024-03-25 | 2025-02-01
60df175e-a9bf-eb11-bacc-000d3a3a8a55 | +Kx0EQodF7Gxr389LlcQ2R+l6HzalYHFNxR6YjSwA3vFPCQ9YgX7LMwPlLht+VMkFnVjqrVEhTFhkV7wcNj06g== | 2024-03-07 09:35 | 2501c | Parenterale legemidler - diverse | Eirik Sverrisson | Maja Monsen | 2022-10-24 | 2023-06-22 | 2024-02-29 | 2025-02-01
caa44911-997c-ee11-8179-6045bd895c76 | dp3XZlzJoc6X+ZTlzc7chjlt7ULajK+S4RVroc3HOYgIf0uw5xPkhABm7sypU6lKCmYdJQJfe/AtBkdp8FHVZA== | 2024-02-19 08:31 | 2501c-1 | Fentanyl | Eirik Sverrisson | Gudrun Gudnadottir | 2023-10-13 | 2023-11-08 | 2024-03-01 | 2025-02-01
77f26ae8-d7cf-ee11-9078-6045bd895c76 | xeRd5y6vbJKYp3q6zJmJBRPE3lq7jqqQb83H3JmmnEW8Pv0pGlARW2LUJx1T1XuKKRtWNV/L7pElRh2RxDeWQQ== | 2024-03-11 10:23 | 2599a | HAE 2599a | Eirik Sverrisson | Tonje Marie Lukkassen | 2024-02-20 | 2024-05-15 | 2024-08-23 | 2025-02-01
4e368fbe-6d71-ee11-8179-6045bd929f12 | E/RhDoMlqKSy2XXRPwydFjBJDLdeEJf4JuLNgH6YDyPeNE8Bonq021pqAoSecS2b7QXV0fItsNeB+lwtvUpApA== | 2024-03-07 09:45 | 2506b | TNF BIO 2506b uten biotilsvarende konkurranse | Eirik Sverrisson | Pål Rydstrøm | 2024-02-29 | 2024-09-02 | 2024-11-15 | 2025-02-01
15c480c5-d4cf-ee11-9079-6045bd895897 | Mj6lga0L5YHJMW8+iCYiuGZ3u6X7Q+iyrPCBXvC/PBnAYX4yaeCYlw6krwSIgbgr7LW3tHbhy9fTlPyTGqXmvQ== | 2024-03-11 10:22 | 2501c-2 | Lakosamid | Eirik Sverrisson | Gudrun Gudnadottir | 2024-02-23 | 2024-03-29 | 2024-06-06 | 2025-02-01
2c5a96ef-4abf-ee11-9078-6045bd895243 | 6xXW3bhA1TWmYC0lpQ2PCXpJOsHTicn3q8cdQNcM+RVdO00UYnzqhfMkzez6h3zsBCOL1ux/ctRZ7Pa8FmvdbQ== | 2024-03-06 09:00 | 2508 | Hepatitt B og C | Lars Hjellup | Anne Helen Ognøy | 2024-01-16 | 2024-09-18 | 2024-11-11 | 2025-04-01
9f33150f-0acf-ee11-9079-6045bd895897 | EvKgGhkSEAlUNs33raqIoL8bjpviiYPttsH3x+1+AyoIVHq60pWpWZwSwulhc+loDe7XTDe9IKWD11H9nBRpxA== | 2024-03-07 09:45 | 2501a-1 | Benzylpenicillin | Eirik Sverrisson | Gudrun Gudnadottir | 2024-02-20 | 2024-04-26 | 2024-06-28 | 2025-04-01
59510c43-0bcf-ee11-9079-6045bd895897 | FKREm1SpS9Ib3exDq3BoQ75nYzWVvGuc1t+W15ChmbjegOTn0qXnWJA7y3Ku4LJql0KQ5iveVvvjVpAn/1Ztbg== | 2024-03-07 09:45 | 2507gj-1 | Anagrelid | Eirik Sverrisson | Gudrun Gudnadottir | 2024-02-23 | 2024-05-03 | 2024-09-13 | 2025-04-01
83e6a6c9-5590-ee11-8179-6045bd929f12 | v4iO2ljrtoBBij9mgnfEmti7XU46Vj+Lw8rf1+9nfZnfH91Jb/nCV4wQDzGBz7ljp0kUpfVH9g8a/9zpYX09sQ== | 2024-03-07 09:40 | Nordisk 2025 | Nordisk 2025 | Eirik Sverrisson | Pål Rydstrøm | 2023-01-12 | 2024-03-04 | 2024-04-26 | 2025-04-01
9e084d7f-8162-ee11-8df0-6045bd895c76 | LEd2ATXIT5VzvZ71W+N/1Z8FSvm8fK6az3hnYdbz5Q9RRRQpM9xFQKsPCO8qHj/PZQWojT+vkGnAfcZIXY5v1A== | 2023-12-06 13:19 | 2505 | MS | Lars Hjellup | Anne Helen Ognøy | 2023-09-25 | 2024-10-15 | 2024-12-02 | 2025-05-01
96fde590-ac6d-ee11-9ae7-6045bd895c76 | DfXNNpYDq76TZXmJFVso121jrHjEVpKmmWm2b9Ut8xNJtliSXIztR4BQowS6H3YAmuKgt9kxwv+YgAFGlpNicw== | 2024-01-02 12:06 | 2527 | Antineovaskulariserende midler | Per Ivar Rivenæs | Erik Hviding | 2024-05-01 | 2024-10-18 | 2024-12-02 | 2025-05-01
8eac33ce-ac6d-ee11-9ae7-6045bd895c76 | buVyKYMt0CBcg/HEitWtyXOXZC3OM5A5N5bKsdob3DpbDHG/qFrL5KewscDJkJKMmICgMXb6WmjWmHKWfeQ2Hw== | 2023-12-04 13:48 | 2599g | Sjeldne sykdommer | Per Ivar Rivenæs | Tonje Marie Lukkassen | 2024-05-01 | 2024-10-18 | 2024-12-02 | 2025-05-01
46bde22f-af6d-ee11-9ae7-6045bd895c76 | J+f63nGLfUEKLZK4C3w0I9BHgwyzTHLC9Agc35HRr1etTo1tVG/JZ3QHENRW+w2n6mTlGFwO9MKnOMlm85h1qg== | 2023-12-04 13:48 | 2599f | Idiopatisk lungefibrose | Per Ivar Rivenæs | Tonje Marie Lukkassen | 2024-05-01 | 2024-10-18 | 2024-12-02 | 2025-05-01
ef91b706-ad6d-ee11-9ae7-6045bd895c76 | e9kmp/0DE2tbNzWf0zerTKB4NEWkpp1kmHiZ5BYhzWPgLZgv30aVx58vbZQ47z6Nzds74Mqne8KjLZHoNYTJIA== | 2023-12-04 13:48 | 2522 | Plasmaderiverte legemidler | Per Ivar Rivenæs | Erik Hviding | 2024-06-01 | 2024-11-18 | 2025-01-02 | 2025-06-01
2ec2b460-6e71-ee11-8179-6045bd929f12 | WP5DWxkueRyNktOhyOaPs8SjoBtYXNRV5ZOtTt9y9cqZK55LWfKFFdLN5OPFR5b2sFODhURGfLZx7ue1FUISRg== | 2024-03-11 10:24 | 2599c | Gaucher | Eirik Sverrisson | Tonje Marie Lukkassen | 2024-08-22 | 2024-11-14 | 2025-01-10 | 2025-06-01
43e4f35b-b571-ee11-8179-6045bd895897 | i7/CjEKMNWn9esphGIlHkqO9WjhvzIQ6/PQ111/jgvU8WuraKZeHemQYGytWxQ88Qwo8U/HOOlUTlRfsniS5JA== | 2024-01-02 12:09 | 2599j | Wilsons sykdom | Per Ivar Rivenæs | Tonje Marie Lukkassen | 2024-09-01 | 2025-02-18 | 2025-04-04 | 2025-09-01
9f370cea-b471-ee11-8179-6045bd895897 | 2AqSDvC4DQdxzKfgrPyxqM7SRpRjU+I9QwIdxcM/INRnw+SzVfvXZbO7HSVLZvx/MhAdrYT6jebZoWEHzVIX0g== | 2023-12-04 13:48 | 2507 | Onkologi | Per Ivar Rivenæs | Helle Nærsnes Endresen | 2024-09-01 | 2025-03-23 | 2025-05-04 | 2025-10-01
ef0ee539-ad6d-ee11-9ae7-6045bd895c76 | X7RIfvzeMqJtF+2OWHuo+SXhJbsT7qKxGEpPVKAbllQoQ35rJI5WbKhPs6I5hfShNPjjnajdUGmXlIXk4r80+w== | 2023-12-04 13:48 | 2599o | Ekulizumab | Per Ivar Rivenæs | Tonje Marie Lukkassen | 2024-10-01 | 2025-03-20 | 2025-05-04 | 2025-10-01
882315ab-ad6d-ee11-9ae7-6045bd895c76 | sDQykYwbsg2GhxNro8TSoI1tObzruJHmW/TuMkqTBbu3yr8uSqvoi0dVz8K48Hx92w8g8nmeSSxpg8cL1l2JDw== | 2023-12-04 13:48 | 2513 | LAR | Per Ivar Rivenæs | Erik Hviding | 2024-11-01 | 2025-03-21 | 2025-05-05 | 2025-11-01
e31aa6d5-ad6d-ee11-9ae7-6045bd895c76 | fkvLIDXpWz+47/8unRUiq9dTqV4qDoLJO1OcLfCHDOvvOYucj983llrvJKvfyVnbrBzX82dhmEKlF49Yo3sABQ== | 2023-12-04 13:48 | 2513-1 | 24t morfin | Per Ivar Rivenæs | Erik Hviding | 2024-11-01 | 2025-04-20 | 2025-06-04 | 2025-11-01
122f3608-ae6d-ee11-9ae7-6045bd895c76 | RUmpl7ueeqcsqbh6Qp/uQgYY4OWGunFfCtX8uDdG/hkJq4bmKPw3Z1xUBGFJ9XXTT3cH1F9pVL+9MCC9iil8yw== | 2023-12-04 13:48 | 2599b | Fabry sykdom | Per Ivar Rivenæs | Tonje Marie Lukkassen | 2024-11-01 | 2025-04-20 | 2025-06-04 | 2025-11-01
7bc3f72f-6f71-ee11-8179-6045bd929f12 | FuIF3deMLW8vk0i/gSbKSIfK/B0wA/zKsZE520LYU7BygSnIxMgblJPheHr535MwEipWc+Ru+cZ+uJw9/7MMJA== | 2024-01-30 14:04 | 2515 | HIV | Eirik Sverrisson | Erik Hviding | 2024-11-01 | 2025-03-14 | 2025-05-16 | 2025-12-01

## hiddenSheet (hidden)
shi_procurement:m99uq68kjr0wpYaZFmxwghwItaRY2laLqP9c3xNERPS6e7RGI0E569stWPQifwcEX4TOucC2ENbJJ2EZD89mgQ==:shi_procurementid=%28Ikke%20endre%29Anskaffelse&checksumLogicalName=%28Ikke%20endre%29Radkontrollsum&modifiedon=%28Ikke%20endre%29Endret%20den&shi_procurement_id=Anskaffelse%20ID&shi_procurement_name=Anskaffelsenavn&shi_division_unit=Divisjons%20Enhet&ownerid=Eier&shi_subject_advisor=Fagr%c3%a5dgiver&shi_jurist=Jurist&shi_procurementstatus=Anskaffelsesstatus&shi_milestone_choice=Milep%c3%a6l%20valg&shi_project_start_planned=Prosjektstart%20planlagt&shi_project_start_revised=Prosjektstart%20revidert&shi_project_start_completed=Prosjektstart%20utf%c3%b8rt&shi_tender_published_planned=Kunngj%c3%b8ring%20planlagt&shi_tender_published_revised=Kunngj%c3%b8ring%20revidert&shi_tender_published_completed=Kunngj%c3%b8ring%20utf%c3%b8rt&shi_estimated_contract_award_date=Avtale%20tildelt%20planlagt&shi_contract_award_date_revised=Avtale%20tildelt%20revidert&shi_actual_contract_award_date=Avtale%20tildelt%20utf%c3%b8rt&shi_estimated_complete_date=Klar%20for%20implementering%20planlagt&shi_complete_date_revised=Klar%20for%20implementering%20revidert&shi_actual_complete_date=Klar%20for%20implementering%20utf%c3%b8rt&shi_contract_valid_from_planned=Virkningsdato%20planlagt&shi_contract_valid_from_revised=Virkningsdato%20revidert&shi_contract_valid_from_completed=Virkningsdato%20utf%c3%b8rt&shi_contract_length_months=Avtalelengde%20i%20m%c3%a5neder&shi_expected_volume=%c3%85rlig%20verdi%20estimert&shi_volume_revised=%c3%85rlig%20verdi%20revidert&shi_return=Gevinst&shi_aggregertrisikovurdering=Aggregert%20risikovurdering&747cbce0-8f50-4b47-9c5c-3bdcae6c9561.shi_confirmedstep=Bekreftet%20steg%20%28Gevinst%29%20%28Gevinstberegning%29&10211117-29f5-448b-9655-2bb4e731a038.shi_risikoniva=Risikoniv%c3%a5%20%28Aggregert%20risikovurdering%29%20%28Risikovurdering%29
Ikke startet | Pågår | Avsluttet | Avlyst
Ikke startet | Prosjektoppstart | Kunngjøring | Avtale tildelt | Avtale signert og klar til implementering | Virkningsdato | Avsluttet | Avlyst
Ikke bekreftet | Steg 1 bekreftet | Steg 2 bekreftet | Steg 1 og 2 bekreftet