## Plan per 01.01.2025
Revidert: 1. januar 2025
(Ikke endre)Anskaffelse | (Ikke endre)Radkontrollsum | (Ikke endre)Endret den | Anskaffelse ID | Anskaffelsenavn | Prosjektleder | Fagrådgiver | Estimert prosjektstart | Estimert kunngjøring | Estimert tildeling | Estimert avtalestart
75ed2227-e795-ef11-8a6a-6045bd9ec6ef | rz7QCOC7XBccn9KFi2NBzu5Xt3J+uCjRNFM+H/76s4Xn7nRxmOaTOeWe9oIzXsfVcwn+DKduPEDXKgfjGv0YJg== | 2024-12-17 09:14 | 2407gj | 2407gj - Cytarabin | Therese Velle | Gudrun Gudnadottir | 2024-10-24 | 2024-10-29 | 2024-11-25 | 2025-01-15
67aa526f-1806-ef11-9f89-0022488c64e2 | soyhYqns0DIloK/CbPd5t9zQGBKw7eglpqounejXWY6K8tT8rCp6Psm7cNXkyM8SbGx6g8k+0FV80k0TMdFPQA== | 2024-11-06 08:11 | 2407gj-2 | Plerixafor | Eirik Sverrisson | Maja Monsen | 2024-04-05 | 2024-05-03 | 2024-10-18 | 2025-02-01
51df175e-a9bf-eb11-bacc-000d3a3a8a55 | igncui47Qi/pwz8+Ky/8C0Op7747UqHV9N/IdQoNg5CkaUwneUpvoUYSyxUHpIFnuB4yQX41k++AVFGzy3KPow== | 2024-10-16 11:34 | 2501a | 2501a Antiinfektiver - diverse | Eirik Sverrisson | Maja Monsen | 2022-10-24 | 2023-09-14 | 2024-03-08 | 2025-02-01
58df175e-a9bf-eb11-bacc-000d3a3a8a55 | YUwH6qU7is9qCOwIYOivUbyejzO4UT7RRVlUXxNuM/7n1/Nm6WvLYPfRcVwvCdjWd+yPHspO04iEBVJuQSw2sg== | 2024-10-16 11:35 | 2501b | 2501b Ikke-parenterale legemidler - diverse | Eirik Sverrisson | Maja Monsen | 2022-10-24 | 2023-10-25 | 2024-04-03 | 2025-02-01
60df175e-a9bf-eb11-bacc-000d3a3a8a55 | sIFHvwfajAlqSSX1m6F7NWliN0LIk92WOEgey61t4BoX0YtJ1XyGp7rXvcWC6F0GYWDA/2cfWEkHPsgw1DJLNg== | 2024-10-16 11:35 | 2501c | 2501c Parenterale legemidler - diverse | Eirik Sverrisson | Maja Monsen | 2022-10-24 | 2023-06-22 | 2024-02-29 | 2025-02-01
caa44911-997c-ee11-8179-6045bd895c76 | QgOjsCd6glozbr4aVFrmrOAwPVhhc3hgDBv+xc8fL3chbcy4sxu96OFeGBPwmKjTwknll1fYvF7PyB3wgUm4AA== | 2024-04-25 13:15 | 2501c-1 | Fentanyl | Eirik Sverrisson | Gudrun Gudnadottir | 2023-10-13 | 2023-11-08 | 2024-02-07 | 2025-02-01
77f26ae8-d7cf-ee11-9078-6045bd895c76 | E5OwCRSwoUPGrTR9h3yK1I9dShdezjQKw6dKNpoR6+B3MN8eTPx0HVtH+G8MqdYWxakmZ8hO7OjptUOu63u5Og== | 2024-12-09 08:08 | 2599a | 2599a HAE | Lars Hjellup | Martin Haugrud Kastnes | 2024-02-20 | 2024-10-27 23:00 | 2024-12-03 23:00 | 2025-02-01
037b715d-2cb6-ef11-b8e8-7c1e524d8d88 | 4/QrKxRjAsE+nvkbZP3hwmbOKG0eSBxORpU3KuOy0tBaMQTLWoY+uGrY1ZybG7nTP/U37vyVqThjj+QxDH08+w== | 2024-12-17 09:12 | 2501c | 2501c - Humanfibrinogen, trombin | Therese Velle | Gudrun Gudnadottir | 2024-12-06 | 2024-12-10 | 2024-12-23 | 2025-02-01
7bc3f72f-6f71-ee11-8179-6045bd929f12 | rks5diMz2mfCtZ4EX15PhrkHO+OLXGYoTYpqKMmwayqscxMSZN1g6P8RVz738mZ+yf3fyxkMO6gghAHnWjCjwQ== | 2024-12-12 07:19 | 2515 | 2515 HIV | Eirik Sverrisson | Erik Hviding | 2024-06-13 | 2025-03-14 | 2025-05-16 | 2025-02-01
46d10aeb-bb87-ef11-ac20-6045bda036be | XuMlEBgS0XzaZR6Dzb3fWK0VeEY84kWanPz1H8HS5bVFvyirZjlRnC9cs2kTH8RC3eoYYuHz/dadQ/GH6z0FRg== | 2024-12-09 13:59 | 2599p | Amifampridin virkestoffkonkurranse | Beate Bjørnstad Løkke | Tonje Marie Lukkassen | 2024-09-30 22:00 | 2024-10-24 22:00 | 2024-12-05 23:00 | 2025-03-01
15a6ca32-3aa3-ef11-8a69-6045bdf26eda | R+N14ocL2YgqLvtn6tG3iCqWn7x5lHtwbNKjA38+Jwcu9xrc7NBX42khp/uF1Um7diZBND4ENcVrjGUEof9uPQ== | 2024-12-10 07:37 | 2562 | 2562 HPV vaksine | Lars Hjellup | Tonje Marie Lukkassen | 2024-02-01 23:00 | 2024-09-15 22:00 | 2025-01-19 23:00 | 2025-03-01
96fde590-ac6d-ee11-9ae7-6045bd895c76 | lu6BrM4DGM9Q36q+G7+hPDXVsS3kbpk3JqjQ1XOvJX+CgroX/dYdWBRxLiwrZ9cXKAlpCvN5+JEuRlGeVPjVxw== | 2024-12-05 14:04 | 2527 | Antineovaskulariserende midler | Piv Rivenæs | Erik Hviding | 2024-06-01 | 2024-10-16 | 2024-12-05 | 2025-03-01
33b4003e-409c-ef11-8a6a-6045bd9ec6ef | OG/7Bryt9IsvbnHaErKYotr18iBPx/fTpDKkQ9Q167h/P+7VioIc4SHzwGDg6T+xg88El2EgFzkAFvnbrVNWaA== | 2024-12-13 13:09 | 2564 | Pneumokokkvaksine VVP | Beate Bjørnstad Løkke | Therese Velle | 2024-10-29 23:00 | 2025-01-19 23:00 | 2025-03-10 23:00 | 2025-04-01
2c5a96ef-4abf-ee11-9078-6045bd895243 | Bhu4RLiZ9ihv6kAJ46ejcLM7Lie3T5mqcgGWSoXPmKblUC92NFmOfHDFV+06aHS4ki7ByqYisW2djI8rT2/Bog== | 2024-12-13 14:03 | 2508 | 2508 Hepatitt B | Lars Hjellup | Anne Helen Ognøy | 2024-01-16 | 2024-06-13 | 2024-09-27 | 2025-04-01
9f33150f-0acf-ee11-9079-6045bd895897 | 5RX4kjYkuxn6jCer9QmFOspI4JGMmRORhs3TeTV5wnso18r1Wunc99v6PkeCjCqzrJ+znw/OMHyOeMMQQlNRwA== | 2024-09-03 08:40 | 2501a-1 | Benzylpenicillin | Eirik Sverrisson | Gudrun Gudnadottir | 2024-02-20 | 2024-04-12 | 2024-06-11 | 2025-04-01
59510c43-0bcf-ee11-9079-6045bd895897 | gv6v8EbzH1BKyeezI4+86grgi7D0JnOe4hkqdv7YSuNN9/t9Sv7SuOoC7Y2r5Fx1U9RCECt0doQhhNkTClduhw== | 2024-09-03 08:40 | 2507gj-1 | Anagrelid | Eirik Sverrisson | Gudrun Gudnadottir | 2024-02-23 | 2024-04-16 | 2024-06-11 | 2025-04-01
81d052ce-5238-ef11-8409-7c1e5225e7fc | pZKOAaEWmvkMWl23MEERO+y9Z/W5A3ebznrElGDJN4eZOmNsRsYhYR1Wl4fN4hYHgJghmRMqG/UyDFntmbF+pg== | 2024-12-13 14:03 | 2508c | 2508c Hepatitt C | Lars Hjellup | Anne Helen Ognøy | 2024-01-16 | 2024-06-13 | 2024-09-27 | 2025-04-01
4e368fbe-6d71-ee11-8179-6045bd929f12 | vhibeBIj9Tqxbj1LMgnr0SWOigInpY0mm75DFWPmWxGeAbTXtbPWqdEL8G5AQIRBBPFFxosJesr59n2rJUd1pQ== | 2024-12-17 08:46 | 2506b | TNF BIO uten biotilsvarende konkurranse | Beate Bjørnstad Løkke | Synne Ildahl Svendsen | 2024-02-29 | 2024-10-30 23:00 | 2025-02-02 23:00 | 2025-05-01
bfe859bf-5bb8-ef11-b8e8-6045bdf26eda | EVH0m6nf1DIyzErIlXbR7OeNUCkZYrELv/fbJfab+u6CaaS3nRLLPLNVswo4ZpvzzL7xhPyt0s39x8k1uWlKig== | 2024-12-12 07:41 | 2505-1 | Natalizumab | Eirik Sverrisson | Anne Helen Ognøy | 2024-11-01 | 2024-12-20 | 2025-03-14 | 2025-05-01
9e084d7f-8162-ee11-8df0-6045bd895c76 | MM1gDLhsZj8GXQpIX/DMEbmM40GOGztlwqyvqpU5cxa+JtdIqrKzee7C0tG81QFvFvT0O1sIXzZKZPI0bZjxfA== | 2024-11-13 10:20 | 2505 | 2505 MS | Eirik Sverrisson | Anne Helen Ognøy | 2023-09-25 | 2024-09-02 | 2024-11-13 | 2025-05-01
a7ac6ebe-726e-ef11-a670-6045bd93911c | /+ybYwJljtJWgwFtWQ75PpgjCr2NkXPbpn81DGlaks/RvOVP8dbFIp/6yHpBB3r8TwnhPD6xCzb5s0Md/q2wtA== | 2024-12-10 14:00 | 2599k | Deferasiroks | Piv Rivenæs | Tonje Marie Lukkassen | 2024-08-01 | 2024-10-04 | 2024-11-20 | 2025-05-01
b8654a60-506f-ef11-a670-6045bd93911c | KmkJphsdaJr+NP6IxvLnZX7rcKObblScUTfaKeHF+bRp9qRUjP65GvK3WuKBvaM1l0P5/vJCe5tuAaVYS4ii8Q== | 2024-12-18 09:30 | 2599m | Sapropterin | Piv Rivenæs | Tonje Marie Lukkassen | 2024-09-01 | 2024-10-04 | 2024-11-25 | 2025-05-01
ab21d399-b4a1-ef11-8a6a-6045bd9ec6ef | VGaTXOdIL6/EdndTevId9xrDpF70bGZk3TcN0SiVNSew5wM7O0QeCCRcq8DFMRh3xYFBULYZPZFP6N8dDEO8Lw== | 2024-11-18 13:32 | 2563 | MMR | Beate Bjørnstad Løkke | Therese Velle | 2024-09-08 22:00 | 2025-01-16 23:00 | 2025-03-13 23:00 | 2025-06-01
27c21d78-a49d-ef11-8a6a-6045bd9ec6ef | AZ/f+e6m4tAcxkhSs+ZxA+eb3q85lXGNPRID4NhNHDHcGNCExTBsTtl27EWNQ/KLXkAuz/7lC429HleXM+QHJw== | 2024-12-13 11:15 | 2565 | BCG | Beate Bjørnstad Løkke | Tonje Marie Lukkassen | 2024-10-31 23:00 | 2025-04-06 22:00 | 2025-06-01 22:00 | 2025-08-08
4bfe029d-fa39-ef11-8409-000d3a296bec | Ys9qhDsxkmLKxxe45WsWanYLH+x/SaHsdm6QP208i23UduMT55BaCESkqzmyEZw7IfPVkHg5/bostzQ0lCvZcw== | 2024-12-17 09:28 | 2512 | 2512 Blodkoagulasjonsfaktorer VIII og vWF | Lars Hjellup | Erik Hviding | 2024-06-25 | 2024-12-12 23:00 | 2025-02-12 | 2025-09-01
ad03f667-ec95-ef11-8a6a-6045bd9ec6ef | +08KjyCXsfihBtPEWX9/oDHLcSqaq2+PvfyLVJ7BSw4H3JZ05PpInkUwdCokAPG+xCWspMSsZksOipXsUFxDeA== | 2024-12-06 10:52 | 2524 | 2524 FDG | Therese Velle | Martin Haugrud Kastnes | 2025-02-04 | 2025-05-23 | 2025-09-02 | 2025-10-01
9f370cea-b471-ee11-8179-6045bd895897 | haa3myp+IAqHmRbKVCvgA8o0rzViUVlUX0sNaGRrrMJYD84Wpvj5YRgGOY9p2uTclA5kJicuD1fnfLOslUwzxQ== | 2024-12-05 14:29 | 2507 | Onkologi | Piv Rivenæs | Helle Nærsnes Endresen | 2024-09-01 | 2025-01-23 | 2025-03-27 | 2025-10-01
204583e6-bdbb-ef11-b8e8-6045bd891238 | Tp5ungq+84Dao0RLUHgmizKTGf2vraGZA5XUjN2HmUK8vmt2m/DAU8DMA46rFSYbwYQZco3RZRmDKJcZ08VJdg== | 2024-12-16 14:57 | 2513a | 2513a LAR | Lars Hjellup | Erik Hviding | 2024-12-15 23:00 | 2025-03-30 22:00 | 2025-06-01 22:00 | 2025-11-01
122f3608-ae6d-ee11-9ae7-6045bd895c76 | 2f57CFNMKAdYx5HPAAVNc2HIVY2bULAK6FbN71uTy/rk6wX8ypjwQzZRoGacNknf850e2qgkSmujSktwYcZIfA== | 2024-12-13 12:13 | 2599b | Fabry sykdom | Beate Bjørnstad Løkke | Martin Haugrud Kastnes | 2025-01-09 23:00 | 2025-04-17 22:00 | 2025-06-04 | 2025-11-01
29555184-5ab9-ef11-b8e8-6045bd8f4284 | IzH2FynhPWaW1w7xTQTqg4U/4lbOMlHmnlQQZgF7mlUHTNzneA7L5LqV8Z9vJbhSYULlmwawWQU4OZk/CtXz1Q== | 2024-12-13 14:02 | 2666 | 2666 DTP-IPV | Lars Hjellup | Therese Velle | 2024-12-01 23:00 | 2025-04-29 22:00 | 2025-09-14 22:00 | 2026-01-01
1ac3561d-50bc-ef11-b8e8-6045bd8f4284 | 7CgrSPz8WXgT88f6g0Blb6rpQOZ0I4ZqhBIBSbHh5/CXg4a3p+FjzYuf9R5kY5v1+ZP5EJmnKz3WOZUvEFW8lQ== | 2024-12-17 08:46 | 2606b | TNF BIO uten biotilsvarende konkurranse | Beate Bjørnstad Løkke | Synne Ildahl Svendsen | 2025-01-08 23:00 | 2025-05-04 22:00 | 2025-06-26 22:00 | 2026-02-01
4df1d840-ad71-ee11-8179-6045bd895897 | iLEBlk5TM2CfQcfNS/bVyHJC3y7GY+egmayVumcSnTeXXl3AkArkmGzYZkoR0BEgi8I1QbncCbcDb+HoRfsf0A== | 2024-12-12 11:18 | 2614 | PAH | Piv Rivenæs | Synne Ildahl Svendsen | 2025-02-01 | 2025-05-07 | 2025-06-24 | 2026-02-01
93213435-abfc-ee11-a1fe-000d3abf6143 | v3p4KRFwvZWtWQQk/GPXjCj39GBC85bdt83KKtBybDtJpILJIuSb5fZNi2BOeabwDJSE/Ntk90nY912TctQkOA== | 2024-10-23 09:11 | 2606a | 2606a TNF BIO med biotilsvarende konkurranse | Eirik Sverrisson | Gudrun Gudnadottir | 2024-04-24 | 2025-03-14 | 2025-06-27 | 2026-02-01
68ec53ae-ac71-ee11-8179-6045bd895897 | pcllEIG+1Zlx06xMOaXmZaSe7AaLdgBfWDJYcvzhyOgd1yNeAKGOEuqrn5rz3Ks48mox0HdMn9wAFiIpph/hOg== | 2024-12-17 10:19 | 2616 | Alvorlig astma | Therese Velle | Pål Rydstrøm | 2025-04-01 | 2025-09-01 | 2025-10-16 | 2026-04-01
b203947a-8c71-ee11-8179-6045bd895897 | NT0PhF1EAo5o2y3XBjsriG/wBLImxpg70yYGI2D0X91QstvQREhngpykBdKKLNioT//cHTeAYl4K5rGHHsvyhw== | 2024-12-12 08:30 | 2632 | 2632 Transplantasjon | Lars Hjellup | Synne Ildahl Svendsen | 2024-10-14 22:00 | 2025-04-27 22:00 | 2025-09-04 22:00 | 2026-04-01
eae239cd-4abc-ef11-b8e8-6045bd8f4284 | Gu1sJEuUnnYWgE44qdh9tv44MeKmzzFiKIpHSyYyMiGZjfdkFwqkZorY4JyOGDk6+K1JhNWFis6fjHjLe/8vOw== | 2024-12-17 07:46 | 2609a | Veksthormonmangel | Beate Bjørnstad Løkke | Therese Velle | 2025-03-31 22:00 | 2025-10-05 22:00 | 2025-11-25 23:00 | 2026-05-01
6c29e78f-b471-ee11-8179-6045bd895897 | PjScACTudWWIUXyMd02KdqVlVsLVMxdl50avYS3fBCdgU6TQ6C+4Jh0vm0d3GWtaRMkABWLkFvDQFqNoFEfoUg== | 2024-11-25 08:46 | 2699l | ITP | Piv Rivenæs | Tonje Marie Lukkassen | 2025-04-01 | 2025-08-20 | 2025-10-07 | 2026-05-01
f1a3d87e-0687-ef11-ac20-7c1e524f9595 | ELG3tr8qHby9T0tVhX2MSxO1GVihaAM/TI516jQJXEQXL4oLjfq+8TV8BkNb/sf7NMM3RvmJxZNhVULa1ssYwg== | 2024-10-10 12:53 | 2699g | Sjeldne sykdommer | Piv Rivenæs | Tonje Marie Lukkassen | 2025-05-01 | 2025-08-15 | 2025-10-01 | 2026-05-01
2d788965-b471-ee11-8179-6045bd895897 | wp9TL44w5Lb/iobGpLVFmpWavzVWDwGzu4Zz8CJUxI7blywbKqlcotg4HVI4+vu6EaehihplLYgciGUfwRFwaQ== | 2024-10-03 11:14 | 2622 | Plasmaderiverte legemidler | Piv Rivenæs | Erik Hviding | 2025-02-01 | 2025-11-18 | 2026-01-02 | 2026-06-01
d4c04347-0787-ef11-ac20-7c1e524f9595 | xyOZ4Z0UHKCBws6PeE0IEIgXWCDemRhbdas+WEPqN7Iyc+mF+vRc6zOmsHxShCiK34cYmHYtZkfCJUKwskxVZQ== | 2024-10-10 12:58 | 2699f | Idiopatisk lungefibrose | Piv Rivenæs | Tonje Marie Lukkassen | 2025-05-06 | 2025-09-01 | 2025-10-22 | 2026-07-01
a77feab9-b471-ee11-8179-6045bd895897 | SCsNa43+wUCRDMpYP3uQVNVDqMgaiLQgbf6y7Xp+0rIT5sC0LY0aBLsl1tCWKMtwc20pGO/NNZnFKUHAajG25A== | 2024-12-17 07:40 | 2609b | Nevroendokrine svulster | Beate Bjørnstad Løkke | Therese Velle | 2025-09-01 | 2026-01-04 23:00 | 2026-03-03 23:00 | 2026-09-01
db02de0d-b571-ee11-8179-6045bd895897 | WGQ+mQeWyU9hVUe3xXSaUeXqUrO53yZk4Cfs69waRWVnIrTdavTiM/TQJ1aMDj+Y96TE4aiCS3d5abYeA7q4bA== | 2024-12-12 07:31 | 2607 | Onkologi | Piv Rivenæs | Helle Nærsnes Endresen | 2025-09-01 | 2026-01-21 | 2026-03-31 | 2026-10-01
c3f20ad0-5fb9-ef11-b8e8-6045bda036be | 97X5czV20BQW05Otu0sDqXSgOxoQq2QTktm27xDqMXr6EX4Bs31o6CFRfjOUAMp2lFBZp5vO3thP0KTLr+ACeQ== | 2024-12-17 10:37 | 2624 | Radiofarmaka | Therese Velle | Martin Haugrud Kastnes | 2025-11-10 | 2026-04-15 | 2026-06-18 | 2026-11-15
bcd9d5b0-6cbc-ef11-b8e8-6045bd8f4284 | JKAEsQ23C/DJNaoGn4bvz4ikCFzUIK1AgBSHwUAqRDY13i/JJEzpubgFB9m8KWHqjoIZdjhFY+C9yGP5Iz6hFg== | 2024-12-17 11:48 | 2699c | Gaucher sykdom | Beate Bjørnstad Løkke | Martin Haugrud Kastnes | 2025-10-30 23:00 | 2026-03-12 23:00 | 2026-05-03 22:00 | 2026-12-01 23:00

## hiddenSheet (hidden)
shi_procurement:6wcIEzXMm6h0AuTzFy6fW66/FLU0jdcEaC3rnPD7+XUqsLn96MAtCVn3cV6DjQFkTdV1yUBB4EFT22efedrisg==:shi_procurementid=%28Ikke%20endre%29Anskaffelse&checksumLogicalName=%28Ikke%20endre%29Radkontrollsum&modifiedon=%28Ikke%20endre%29Endret%20den&shi_procurement_id=Anskaffelse%20ID&shi_procurement_name=Anskaffelsenavn&shi_division_unit=Divisjons%20Enhet&ownerid=Eier&shi_subject_advisor=Fagr%c3%a5dgiver&shi_jurist=Jurist&shi_procurementstatus=Anskaffelsesstatus&shi_milestone_choice=Milep%c3%a6l%20valg&shi_project_start_planned=Prosjektstart%20planlagt&shi_project_start_revised=Prosjektstart%20revidert&shi_project_start_completed=Prosjektstart%20utf%c3%b8rt&shi_tender_published_planned=Kunngj%c3%b8ring%20planlagt&shi_tender_published_revised=Kunngj%c3%b8ring%20revidert&shi_tender_published_completed=Kunngj%c3%b8ring%20utf%c3%b8rt&shi_estimated_contract_award_date=Avtale%20tildelt%20planlagt&shi_contract_award_date_revised=Avtale%20tildelt%20revidert&shi_actual_contract_award_date=Avtale%20tildelt%20utf%c3%b8rt&shi_estimated_complete_date=Klar%20for%20implementering%20planlagt&shi_complete_date_revised=Klar%20for%20implementering%20revidert&shi_actual_complete_date=Klar%20for%20implementering%20utf%c3%b8rt&shi_contract_valid_from_planned=Virkningsdato%20planlagt&shi_contract_valid_from_revised=Virkningsdato%20revidert&shi_contract_valid_from_completed=Virkningsdato%20utf%c3%b8rt&shi_contract_length_months=Avtalelengde%20i%20m%c3%a5neder&shi_expected_volume=%c3%85rlig%20verdi%20estimert&shi_volume_revised=%c3%85rlig%20verdi%20revidert&shi_return=Gevinst&shi_aggregertrisikovurdering=Aggregert%20risikovurdering&747cbce0-8f50-4b47-9c5c-3bdcae6c9561.shi_confirmedstep=Bekreftet%20steg%20%28Gevinst%29%20%28Gevinstberegning%29&10211117-29f5-448b-9655-2bb4e731a038.shi_risikoniva=Risikoniv%c3%a5%20%28Aggregert%20risikovurdering%29%20%28Risikovurdering%29
Ikke startet | Pågår | Avsluttet | Avlyst
Ikke startet | Prosjektoppstart | Kunngjøring | Avtale tildelt | Avtale signert og klar til implementering | Virkningsdato | Avsluttet | Avlyst
Ikke bekreftet | Steg 1 bekreftet | Steg 2 bekreftet | Steg 1 og 2 bekreftet